## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | team-swen-261-2B-Crocky's-Cohorts
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | ISM; 3/15/2022; user and admin can both naviagate to products page
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | ISM; 3/15/2022; add descriptions
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass
As a Owner I want to see a list of the inventory so I may edit products | Given that I can log in, when I input admin, then I am taken to a page where I can see the products in the inventory | Pass | ISM; 3/15/2022; Can see inventory
| Given I can log in as an admin, when I am on the inventory page, I can select a product and see its details | Pass | ISM;3/15/2022; Can see details
| Given I can log in as an admin, when I am on the inventory page, I can select a product and edit its details | Pass | ISM; 3/15/2022; Can edit details