## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | team-swen-261-2B-Crocky's-Cohorts
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | ISM; 3/15/2022; user and admin can both naviagate to products page
| Given that I am logged in when I am on anypage, then I should be able to logout | Pass | ADV; 3/15/2022; If the user is logged in, there is a logout button on every page
| Given that I am not logged in when I am on any page, then I should be able to login. | Pass | ADV; 3/15/2022; If the user is not logged in, there is a login button on every page
| Given that I am not logged in when I attempt to login, then I should be able to login or create an account. | Pass | ADV; 3/15/2022; Login works
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | ADV; 3/15/2022; Clicking the products page button will take the user to the products page
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | ADV; 3/15/2022; Message displays in the message board
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | ISM; 3/15/2022; add descriptions
| Given that I am a Customer that is logged in when I am on the products page then I should have the ability to search for a product | Pass | ADV; 3/15/2022; Product search bar works for customers
| Given I am a Customer that is logged in when I have logged in then I should have the ability to access my shopping cart | Pass | ADV; 3/15/2022; If the user is logged in, there is a shopping cart button on every page
| Given that I am a Customer that is logged in, when I am on a product's page, then I can add the product to my shopping cart. | Fail | ADV; 3/15/2022; Adding a product to the shopping cart only stores the information in the front-end and does not save to the backend.
| Given that I am a Cutomer that is logged in, when I am on on my shopping cart page, then I can remove products from my shopping cart. | Fail | ADV; 3/15/2022; Same issue as adding a products. All the information in the front-end is not saved in the back-end.
As a Owner I want to see a list of the inventory so I may edit products | Given that I can log in, when I input admin, then I am taken to a page where I can see the products in the inventory | Pass | ISM; 3/15/2022; Can see inventory
| Given I am logged in as an admin, when I am on the inventory page, then I can select a product and see its details | Pass | ISM;3/15/2022; Can see details
| Given I am logged in as an admin, when I am on the inventory page, then I can select a product and edit its details | Pass | ISM; 3/15/2022; Can edit details
| Given I am logged in as an admin, when I am on the inventory page, then I can remove a product | Pass | ADV; 3/15/2022; Can remove a product
| Given I log in as an admin, when I am on the inventory page, then I can add a product a fill in the product's details | Fail | ADV; 3/15/2022; We can create a new product, but the front-end is nor properly connected with the back-end, so no information is actually updated to be saved.
| Given I am logged in as an admin, when I am on any page, then I cannot access a shopping cart | Pass | ADV; 3/15/2022; When an admin, there is no shopping cart button